## Road Map
Cloud-based Accounting System (Xero)
Release 1
Application Modules | Feature Backlog | Story Points | Cycle 1 - 04/19/24 | Cycle 2 - 05/03/24 | Cycle 3 - 05/10/24
Module 08 - Purchase Orders | 08.01 Create Purchase Order | 2 | X
| 08.02 Edit Purchase Order | 2 | X
| 08.03 Delete Purchase Order | 2 | X
| 08.04 View Purchase Order | 1 | X
| 08.05 View List of Purchase Order(s) | 1 | X
| 08.06 Search Purchase Orders | 1 | X
| 08.07 Filter Purchase Order(s) by Status | 1 | X
| 08.08 Sort by Number, Reference, Supplier, Date Raised, Delivery Date | 1 | X
| 08.09 Print Purchase Order | 2 | X
| 08.10 Send a Purchase Order | 3 | X
| 08.11 Copy Contents for a New Bill, a New Purchase Order, generating an Invoice | 5 | X
| 08.12 Upload Files or Add Files from the Library | 2 | X
| 08.13 Filter Purchase Orders | 1 | X
| 08.14 Approve a Purchase Order | 3 | X
| 08.15 Bill a Purchase Order | 4 | X
| 08.16 Add a Note to Purchase Order | 1 | X
| 08.17 Track Purchase Order History | 4 | X
Module 09 - Expense Claims | 09.01 Create Expense Claim | 3 |  | X
| 09.02 Create Mileage Claim | 4 |  | X
| 09.03 Edit Expense Claim | 2 |  | X
| 09.04 Delete Expense Claim | 2 |  | X
| 09.05 Review Expense Claims | 3 |  | X
| 09.06 Approve Expense Claims | 2 |  | X
| 09.07 Decline Expense Claims | 2 |  | X
| 09.08 Pay Expense Claims | 4 |  | X
| 09.09 View Expense Claims | 3 |  | X
| 09.10 Explore Expense Claims | 4 |  | X
Module 11 - Accounts Payable | 11.01 Recording Vendor Bills | 1 |  |  | X
| 11.02 Reviewing Bills for Goods/Services Receipt | 3 |  |  | X
| 11.03 Scheduling Payments According to Vendor Terms | 5 |  |  | X
| 11.04 Disbursement of Payments | 2 |  |  | X
| 11.05 Updating Books to reflect Paid Bills | 3 |  |  | X
| 11.06 Adding Unpaid Bills to the Accounts Payable | 3 |  |  | X
| 11.07 Create Supplier | 3 |  |  | X
| 11.08 Edit Supplier | 2 |  |  | X
| 11.09 Archive Supplier | 2 |  |  | X
| 11.10 View Contacts | 1 |  |  | X
| 11.11 Search Contacts | 2 |  |  | X
|  | VELOCITY: | 36 | 29 | 27