## Sheet1
Project | Module | Release | Test Run Log Release | Test Suite | Test Run | Test Run Type | Test Case | Test Case Type | Planned Start Date | Execution Start Date | Tester | Result | Requirements | Defects (qTest)
Team 3 | 09. Expense Claims | Iteration 2 | Iteration 2 | Sandeep | TC8. Pay Expense Claim - Access Control and Permissions for Paying Expense Claims | Functional | TC8. Pay Expense Claim - Access Control and Permissions for Paying Expense Claims | Manual | 2024-05-02 | 2024-05-02 | Sai Sandeep Mandava | Passed | 1 | 0
Team 3 | 09. Expense Claims | Iteration 2 | Iteration 2 | Sandeep | TC8. Pay Expense Claim - Access Control and Permissions for Paying Expense Claims | Functional | TC8. Pay Expense Claim - Access Control and Permissions for Paying Expense Claims | Manual | 2024-05-02 | 2024-05-02 | Sai Sandeep Mandava | Failed | 1 | 0
Team 3 | 09. Expense Claims | Iteration 2 | Iteration 2 | Sandeep | TC8. Pay Expense Claim - Access Control and Permissions for Paying Expense Claims | Functional | TC8. Pay Expense Claim - Access Control and Permissions for Paying Expense Claims | Manual | 2024-05-02 | 2024-05-02 | Sai Sandeep Mandava | Passed | 1 | 0
Team 3 | 09. Expense Claims | Iteration 2 | Iteration 2 | Sandeep | TC7. Pay Expense Claim - Pay Multiple Expense Claims Simultaneously " | Functional | TC7. Pay Expense Claim - Pay Multiple Expense Claims Simultaneously " | Manual | 2024-05-02 | 2024-05-02 | Sai Sandeep Mandava | Passed | 1 | 0
Team 3 | 09. Expense Claims | Iteration 2 | Iteration 2 | Sandeep | TC7. Pay Expense Claim - Pay Multiple Expense Claims Simultaneously " | Functional | TC7. Pay Expense Claim - Pay Multiple Expense Claims Simultaneously " | Manual | 2024-05-02 | 2024-05-02 | Sai Sandeep Mandava | Passed | 1 | 0
Team 3 | 09. Expense Claims | Iteration 2 | Iteration 2 | Sandeep | TC9. Pay Expense Claim -Data Integrity Check for Expense Claim Payments | Functional | TC9. Pay Expense Claim -Data Integrity Check for Expense Claim Payments | Manual | 2024-05-02 | 2024-05-02 | Sai Sandeep Mandava | Failed | 1 | 0
Team 3 | 09. Expense Claims | Iteration 2 | Iteration 2 | Sandeep | TC6. Pay Expense Claim - Pay a Single Expense Claim | Functional | TC6. Pay Expense Claim - Pay a Single Expense Claim | Manual | 2024-05-02 | 2024-05-02 | Sai Sandeep Mandava | Passed | 1 | 0
Team 3 | 09. Expense Claims | Iteration 2 | Iteration 2 | Sandeep | TC6. Pay Expense Claim - Pay a Single Expense Claim | Functional | TC6. Pay Expense Claim - Pay a Single Expense Claim | Manual | 2024-05-02 | 2024-05-02 | Sai Sandeep Mandava | Passed | 1 | 0
Team 3 | 09. Expense Claims | Iteration 2 | Iteration 2 | Sandeep | TC10. Pay Expense Claim - Expense Claim Payment Processing under Network Variability | Functional | TC10. Pay Expense Claim - Expense Claim Payment Processing under Network Variability | Manual | 2024-05-02 | 2024-05-02 | Sai Sandeep Mandava | Passed | 1 | 0
Team 3 | 09. Expense Claims | Iteration 2 | Iteration 2 | Sakshi | TC11. Approve Expense Claim - GUI Testing | Functional | TC11. Approve Expense Claim - GUI Testing | Manual | 2024-05-02 | 2024-05-05 | Sakshi Singh | Passed | 1 | 0
Team 3 | 09. Expense Claims | Iteration 2 | Iteration 2 | Rahul | TC1. Explore Expense Claim - Explore and View Expense Claims | Functional | TC1. Explore Expense Claim - Explore and View Expense Claims | Manual | 2024-05-02 | 2024-05-05 | Sai Sandeep Mandava | Passed | 1 | 0
Team 3 | 09. Expense Claims | Iteration 2 | Iteration 2 | Rahul | TC3. Explore Expense Claim - Filter Expense Claims by Status | Functional | TC3. Explore Expense Claim - Filter Expense Claims by Status | Manual | 2024-05-02 | 2024-05-05 | Sai Sandeep Mandava | Passed | 1 | 0
Team 3 | 09. Expense Claims | Iteration 2 | Iteration 2 | Madhu | TC6. View Exoense Claims-Data flow-in | Functional | TC6. View Exoense Claims-Data flow-in | Manual | 2024-05-02 | 2024-05-05 | Sai Sandeep Mandava | Passed | 1 | 0
Team 3 | 09. Expense Claims | Iteration 2 | Iteration 2 | Rahul | TC5. Explore Expense Claim -Expense Claims Functionality under Network Variability | Functional | TC5. Explore Expense Claim -Expense Claims Functionality under Network Variability | Manual | 2024-05-02 | 2024-05-05 | Sai Sandeep Mandava | Passed | 1 | 0
Team 3 | 09. Expense Claims | Iteration 2 | Iteration 2 | Rahul | TC2. Explore Expense Claim - Submit and Approve Expense Claims | Functional | TC2. Explore Expense Claim - Submit and Approve Expense Claims | Manual | 2024-05-02 | 2024-05-05 | Sai Sandeep Mandava | Passed | 1 | 0
Team 3 | 09. Expense Claims | Iteration 2 | Iteration 2 | Madhu | TC4.View Expense Claims - STS-Status | Functional | TC4.View Expense Claims - STS-Status | Manual | 2024-05-02 | 2024-05-05 | Sai Sandeep Mandava | Passed | 1 | 0
Team 3 | 09. Expense Claims | Iteration 2 | Iteration 2 | Rahul | TC4. Explore Expense Claim - Access Control Based on User Roles | Functional | TC4. Explore Expense Claim - Access Control Based on User Roles | Manual | 2024-05-02 | 2024-05-05 | Sai Sandeep Mandava | Passed | 1 | 0
Team 3 | 09. Expense Claims | Iteration 2 | Iteration 2 | Madhu | TC3.View Expense Claims-ET-Entitlements | Functional | TC3.View Expense Claims-ET-Entitlements | Manual | 2024-05-02 | 2024-05-05 | Sai Sandeep Mandava | Passed | 1 | 0
Team 3 | 09. Expense Claims | Iteration 2 | Iteration 2 | Madhu | TC2. View Expense Claims - Core Functionality Testing | Functional | TC2. View Expense Claims - Core Functionality Testing | Manual | 2024-05-02 | 2024-05-05 | Sai Sandeep Mandava | Passed | 1 | 0
Team 3 | 09. Expense Claims | Iteration 2 | Iteration 2 | Madhu | TC1. View Expense Claims - GUI Testing | Functional | TC1. View Expense Claims - GUI Testing | Manual | 2024-05-02 | 2024-05-05 | Sai Sandeep Mandava | Passed | 1 | 0
Team 3 | 09. Expense Claims | Iteration 2 | Iteration 2 | Madhu | TC5. View Expense Claims-CN-connetivity | Functional | TC5. View Expense Claims-CN-connetivity | Manual | 2024-05-02 | 2024-05-05 | Sai Sandeep Mandava | Passed | 1 | 0
Team 3 | 09. Expense Claims | Iteration 2 | Iteration 2 | Sakshi | TC13. Approve Expense Claim - Access Control Based on User Roles | Functional | TC13. Approve Expense Claim - Access Control Based on User Roles | Manual | 2024-05-02 | 2024-05-05 | Sakshi Singh | Passed | 1 | 0
Team 3 | 09. Expense Claims | Iteration 2 | Iteration 2 | Sakshi | TC12. Approve Expense Claim - Core Functionality Testing | Functional | TC12. Approve Expense Claim - Core Functionality Testing | Manual | 2024-05-02 | 2024-05-05 | Sakshi Singh | Passed | 1 | 0
Team 3 | 09. Expense Claims | Iteration 2 | Iteration 2 | Sakshi | TC14. Approve Expense Claim - Status Testing | Functional | TC14. Approve Expense Claim - Status Testing | Manual | 2024-05-02 | 2024-05-05 | Sakshi Singh | Passed | 1 | 0
Team 3 | 09. Expense Claims | Iteration 2 | Iteration 2 | Sakshi | TC15. Approve Expense Claim - Concurrent Status Update Testing | Functional | TC15. Approve Expense Claim - Concurrent Status Update Testing | Manual | 2024-05-02 | 2024-05-05 | Sakshi Singh | Failed | 1 | 1
Team 3 | 09. Expense Claims | Iteration 2 | Iteration 2 | Sakshi | TC16. Approve Expense Claim -Expense Claims Functionality Under Network Variability | Functional | TC16. Approve Expense Claim -Expense Claims Functionality Under Network Variability | Manual | 2024-05-02 | 2024-05-05 | Sakshi Singh | Passed | 1 | 0
Team 3 | 09. Expense Claims | Iteration 2 | Iteration 2 | Sakshi | TC18. Decline Expense Claim - Core Functionality Testing | Functional | TC18. Decline Expense Claim - Core Functionality Testing | Manual | 2024-05-02 | 2024-05-05 | Sakshi Singh | Passed | 1 | 0
Team 3 | 09. Expense Claims | Iteration 2 | Iteration 2 | Sakshi | TC17. Decline Expense Claim - GUI Testing | Functional | TC17. Decline Expense Claim - GUI Testing | Manual | 2024-05-02 | 2024-05-05 | Sakshi Singh | Passed | 1 | 0
Team 3 | 09. Expense Claims | Iteration 2 | Iteration 2 | Sakshi | TC19. Decline Expense Claim - Access Control Based on User Roles | Functional | TC19. Decline Expense Claim - Access Control Based on User Roles | Manual | 2024-05-02 | 2024-05-05 | Sakshi Singh | Passed | 1 | 0
Team 3 | 09. Expense Claims | Iteration 2 | Iteration 2 | Sakshi | TC20. Decline Expense Claim - Status Testing | Functional | TC20. Decline Expense Claim - Status Testing | Manual | 2024-05-02 | 2024-05-05 | Sakshi Singh | Passed | 1 | 0
Team 3 | 09. Expense Claims | Iteration 2 | Iteration 2 | Sakshi | TC21. Decline Expense Claim - Field Validation Testing | Functional | TC21. Decline Expense Claim - Field Validation Testing | Manual | 2024-05-02 | 2024-05-05 | Sakshi Singh | Failed | 1 | 2
Team 3 | 09. Expense Claims | Iteration 2 | Iteration 2 | Sakshi | TC23. Decline Expense Claim -Expense Claims Functionality Under Network Variability | Functional | TC23. Decline Expense Claim -Expense Claims Functionality Under Network Variability | Manual | 2024-05-02 | 2024-05-05 | Sakshi Singh | Passed | 1 | 0
Team 3 | 09. Expense Claims | Iteration 2 | Iteration 2 | Sakshi | TC22. Decline Expense Claim - Concurrent Status Update Testing | Functional | TC22. Decline Expense Claim - Concurrent Status Update Testing | Manual | 2024-05-02 | 2024-05-05 | Sakshi Singh | Failed | 1 | 1
Team 3 | 09. Expense Claims | Iteration 2 | Iteration 2 | Sandeep | TC8. Pay Expense Claim - Access Control and Permissions for Paying Expense Claims | Functional | TC8. Pay Expense Claim - Access Control and Permissions for Paying Expense Claims | Manual | 2024-05-02 | 2024-05-05 | Sai Sandeep Mandava | Passed | 1 | 0
Team 3 | 09. Expense Claims | Iteration 2 | Iteration 2 | Sandeep | TC9. Pay Expense Claim -Data Integrity Check for Expense Claim Payments | Functional | TC9. Pay Expense Claim -Data Integrity Check for Expense Claim Payments | Manual | 2024-05-02 | 2024-05-05 | Sai Sandeep Mandava | Passed | 1 | 0
Team 3 | 09. Expense Claims | Iteration 2 | Iteration 2 | Sandeep | TC6. Pay Expense Claim - Pay a Single Expense Claim | Functional | TC6. Pay Expense Claim - Pay a Single Expense Claim | Manual | 2024-05-02 | 2024-05-05 | Sai Sandeep Mandava | Passed | 1 | 0
Team 3 | 09. Expense Claims | Iteration 2 | Iteration 2 | Sandeep | TC7. Pay Expense Claim - Pay Multiple Expense Claims Simultaneously " | Functional | TC7. Pay Expense Claim - Pay Multiple Expense Claims Simultaneously " | Manual | 2024-05-02 | 2024-05-05 | Sai Sandeep Mandava | Passed | 1 | 0
Team 3 | 09. Expense Claims | Iteration 2 | Iteration 2 | Sandeep | TC10. Pay Expense Claim - Expense Claim Payment Processing under Network Variability | Functional | TC10. Pay Expense Claim - Expense Claim Payment Processing under Network Variability | Manual | 2024-05-02 | 2024-05-05 | Sai Sandeep Mandava | Passed | 1 | 0
Team 3 | 09. Expense Claims | Iteration 2 | Iteration 2 | Tanzil | TC1. Create Mileage Claim - GUI Testing | Functional | TC1. Create Mileage Claim - GUI Testing | Manual | 2024-05-02 | 2024-05-05 | Sai Sandeep Mandava | Passed | 1 | 0
Team 3 | 09. Expense Claims | Iteration 2 | Iteration 2 | Tanzil | TC2. Create Mileage Claim - Core Functionality Testing | Functional | TC2. Create Mileage Claim - Core Functionality Testing | Manual | 2024-05-02 | 2024-05-05 | Sai Sandeep Mandava | Passed | 1 | 0
Team 3 | 09. Expense Claims | Iteration 2 | Iteration 2 | Tanzil | TC6. Create mileage Claim - Field Validation "Description" | Functional | TC6. Create mileage Claim - Field Validation "Description" | Manual | 2024-05-02 | 2024-05-05 | Tanzil Bilal Mohammed | Passed | 1 | 1
Team 3 | 09. Expense Claims | Iteration 2 | Iteration 2 | Tanzil | TC7. Create Mileage Claim - Field Validation "Travelled on" | Functional | TC7. Create Mileage Claim - Field Validation "Travelled on" | Manual | 2024-05-02 | 2024-05-05 | Tanzil Bilal Mohammed | Passed | 1 | 1
Team 3 | 09. Expense Claims | Iteration 2 | Iteration 2 | Tanzil | TC8. Create Mileage Claim - Field Validation "Account" | Functional | TC8. Create Mileage Claim - Field Validation "Account" | Manual | 2024-05-02 | 2024-05-05 | Tanzil Bilal Mohammed | Passed | 1 | 0
Team 3 | 09. Expense Claims | Iteration 2 | Iteration 2 | Tanzil | TC11. Create Mileage Claim - Calculation Testing | Functional | TC11. Create Mileage Claim - Calculation Testing | Manual | 2024-05-02 | 2024-05-05 | Tanzil Bilal Mohammed | Passed | 1 | 0
Team 3 | 09. Expense Claims | Iteration 2 | Iteration 2 | Tanzil | TC9. Create Mileage Claim - Entitlements Testing | Functional | TC9. Create Mileage Claim - Entitlements Testing | Manual | 2024-05-02 | 2024-05-05 | Tanzil Bilal Mohammed | Passed | 1 | 0
Team 3 | 09. Expense Claims | Iteration 2 | Iteration 2 | Tanzil | TC13. Create Mileage Claim - Data Flow-Out Testing | Functional | TC13. Create Mileage Claim - Data Flow-Out Testing | Manual | 2024-05-02 | 2024-05-05 | Tanzil Bilal Mohammed | Passed | 1 | 0
Team 3 | 09. Expense Claims | Iteration 2 | Iteration 2 | Tanzil | TC1. Create Mileage Claim - GUI Testing | Functional | TC1. Create Mileage Claim - GUI Testing | Manual | 2024-05-02 | 2024-05-05 | Tanzil Bilal Mohammed | Passed | 1 | 0
Team 3 | 09. Expense Claims | Iteration 2 | Iteration 2 | Tanzil | TC2. Create Mileage Claim - Core Functionality Testing | Functional | TC2. Create Mileage Claim - Core Functionality Testing | Manual | 2024-05-02 | 2024-05-05 | Tanzil Bilal Mohammed | Passed | 1 | 0
Team 3 | 09. Expense Claims | Iteration 2 | Iteration 2 | Tanzil | TC3. Create Mileage Claim - Status Validation | Functional | TC3. Create Mileage Claim - Status Validation | Manual | 2024-05-02 | 2024-05-05 | Tanzil Bilal Mohammed | Passed | 1 | 0
Team 3 | 09. Expense Claims | Iteration 2 | Iteration 2 | Tanzil | TC4. Create Mileage Claim - Field Validation "Mileage Claim" | Functional | TC4. Create Mileage Claim - Field Validation "Mileage Claim" | Manual | 2024-05-02 | 2024-05-05 | Tanzil Bilal Mohammed | Passed | 1 | 0
Team 3 | 09. Expense Claims | Iteration 2 | Iteration 2 | Tanzil | TC5. Create Mileage Claim - Field Validation "Rate in USD" | Functional | TC5. Create Mileage Claim - Field Validation "Rate in USD" | Manual | 2024-05-02 | 2024-05-05 | Tanzil Bilal Mohammed | Passed | 1 | 0
Team 3 | 09. Expense Claims | Iteration 2 | Iteration 2 | Tanzil | TC12. Create Mileage Claim - Connectivity Testing | Functional | TC12. Create Mileage Claim - Connectivity Testing | Manual | 2024-05-02 | 2024-05-05 | Tanzil Bilal Mohammed | Passed | 1 | 0
Team 3 | 09. Expense Claims | Iteration 2 | Iteration 2 | Tanzil | TC10. Create Mileage Claim - Data-Driven Defaults Testing | Functional | TC10. Create Mileage Claim - Data-Driven Defaults Testing | Manual | 2024-05-02 | 2024-05-05 | Tanzil Bilal Mohammed | Passed | 1 | 0