## Sheet1
Project | Module | Release | Requirement | Type | Priority | Status | Creator | Created Date | Last Modified Date | Manual Test Cases | Manual Test Runs | Automated Test Cases | Automated Test Runs | Total Runs Passed | Total Runs Failed | Defects (qTest) | Defects (Linked)
Team30G1 | 08. Purchase Order |  | 08.12 Upload Files or Add Files from the Library | Functional | Must have | New | Tarjanee Desai | 2024-04-19 | 2024-04-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team30G1 | 08. Purchase Order |  | 08.12 Upload Files or Add Files from the Library | Functional | Must have | New | Tarjanee Desai | 2024-04-19 | 2024-04-23 | 7 | 7 | 0 | 0 | 7 | 0 | 0 | 0
Team30G1 | 08. Purchase Order |  | 08.01 Create Purchase Order | Functional | Must have | New | Shloka Gupta | 2024-04-18 | 2024-04-20 | 19 | 19 | 0 | 0 | 16 | 3 | 3 | 0
Team30G1 | 08. Purchase Order |  | 08.03 Delete Purchase Order | Functional | Must have | New | Shloka Gupta | 2024-04-18 | 2024-04-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team30G1 | 08. Purchase Order |  | 08.04 View Purchase Order | Functional | Must have | New | Tarjanee Desai | 2024-04-19 | 2024-04-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team30G1 | 08. Purchase Order |  | 08.11 Copy Contents for a New Bill, a New Purchase Order, generating an Invoice | Functional | Must have | New | Tarjanee Desai | 2024-04-19 | 2024-04-20 | 6 | 6 | 0 | 0 | 6 | 0 | 0 | 0
Team30G1 | 08. Purchase Order |  | 08.16 Add a Note to Purchase Order | Functional | Must have | New | Tarjanee Desai | 2024-04-19 | 2024-04-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team30G1 | 08. Purchase Order |  | 08.02 Edit Purchase Order | Functional | Must have | New | Shloka Gupta | 2024-04-18 | 2024-04-20 | 21 | 21 | 0 | 0 | 18 | 3 | 3 | 0
Team30G1 | 08. Purchase Order |  | 08.05 View List of Purchase Order(s) | Functional | Must have | New | Tarjanee Desai | 2024-04-19 | 2024-04-20 | 5 | 5 | 0 | 0 | 5 | 0 | 0 | 0
Team30G1 | 08. Purchase Order |  | 08.06 Search Purchase Orders | Functional | Must have | New | Tarjanee Desai | 2024-04-19 | 2024-04-20 | 4 | 4 | 0 | 0 | 4 | 0 | 0 | 0
Team30G1 | 08. Purchase Order |  | 08.17 Track Purchase Order History | Functional | Must have | New | Tarjanee Desai | 2024-04-19 | 2024-04-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team30G1 | 08. Purchase Order |  | 08.15 Bill a Purchase Order | Functional | Must have | New | Tarjanee Desai | 2024-04-19 | 2024-04-29 | 8 | 8 | 0 | 0 | 8 | 0 | 0 | 0
Team30G1 | 08. Purchase Order |  | 08.10 Send a Purchase Order | Functional | Must have | New | Tarjanee Desai | 2024-04-23 | 2024-04-23 | 7 | 7 | 0 | 0 | 7 | 0 | 0 | 0
Team30G1 | 08. Purchase Order |  | 08.08 Sort by Number, Reference, Supplier, Date Raised, Delivery Date | Functional | Must have | New | Tarjanee Desai | 2024-04-19 | 2024-04-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team30G1 | 08. Purchase Order |  | 08.14 Approve a Purchase Order | Functional | Must have | New | Tarjanee Desai | 2024-04-19 | 2024-04-29 | 7 | 7 | 0 | 0 | 7 | 0 | 0 | 0
Team30G1 | 08. Purchase Order |  | 08.09 Print Purchase Order | Functional | Must have | New | Tarjanee Desai | 2024-04-19 | 2024-04-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team30G1 | 08. Purchase Order |  | 08.13 Filter Purchase Orders | Functional | Must have | New | Tarjanee Desai | 2024-04-19 | 2024-04-20 | 4 | 8 | 0 | 0 | 8 | 0 | 0 | 0
Team30G1 | 08. Purchase Order |  | 08.07 Filter Purchase Order(s) by Status | Functional | Must have | New | Tarjanee Desai | 2024-04-19 | 2024-04-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team30G1 | 09. Expense Claims |  | 09.03 Edit Expense Claims | Functional | Must have | New | Tarjanee Desai | 2024-04-19 | 2024-04-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team30G1 | 09. Expense Claims |  | 09.05 Review Expense Claims | Functional | Must have | New | Tarjanee Desai | 2024-04-19 | 2024-04-29 | 5 | 5 | 0 | 0 | 5 | 0 | 0 | 0
Team30G1 | 09. Expense Claims |  | 09.10 Explore Expense Claims | Functional | Must have | New | Tarjanee Desai | 2024-04-19 | 2024-04-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team30G1 | 09. Expense Claims |  | 09.04 Delete Expense Claims | Functional | Must have | New | Tarjanee Desai | 2024-04-19 | 2024-04-20 | 7 | 7 | 0 | 0 | 7 | 0 | 0 | 0
Team30G1 | 09. Expense Claims |  | 09.06 Approve Expense Claims | Functional | Must have | New | Tarjanee Desai | 2024-04-19 | 2024-04-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team30G1 | 09. Expense Claims |  | 09.07 Decline Expense Claims | Functional | Must have | New | Tarjanee Desai | 2024-04-19 | 2024-04-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team30G1 | 09. Expense Claims |  | 09.01 Create Expense Claim | Functional | Must have | New | Tarjanee Desai | 2024-04-19 | 2024-04-28 | 15 | 15 | 0 | 0 | 13 | 2 | 2 | 0
Team30G1 | 09. Expense Claims |  | 09.02 Create Mileage Claim | Functional | Must have | New | Tarjanee Desai | 2024-04-19 | 2024-04-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team30G1 | 09. Expense Claims |  | 09.08 Pay Expense Claims | Functional | Must have | New | Tarjanee Desai | 2024-04-19 | 2024-04-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team30G1 | 09. Expense Claims |  | 09.09 View Expense Claims | Functional | Must have | New | Tarjanee Desai | 2024-04-19 | 2024-04-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team30G1 | 11. Accounts Payable |  | 11.01 Recording Vendor Bills | Functional | Must have | New | Tarjanee Desai | 2024-04-19 | 2024-04-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team30G1 | 11. Accounts Payable |  | 11.05 Updating Books to reflect Paid Bills | Functional | Must have | New | Tarjanee Desai | 2024-04-19 | 2024-04-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team30G1 | 11. Accounts Payable |  | 11.06 Adding Unpaid Bills to the Accounts Payable | Functional | Must have | New | Tarjanee Desai | 2024-04-19 | 2024-04-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team30G1 | 11. Accounts Payable |  | 11.10 View Contacts | Functional | Must have | New | Tarjanee Desai | 2024-04-19 | 2024-04-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team30G1 | 11. Accounts Payable |  | 11.04 Disbursement of Payments | Functional | Must have | New | Tarjanee Desai | 2024-04-19 | 2024-04-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team30G1 | 11. Accounts Payable |  | 11.11 Search Contacts | Functional | Must have | New | Tarjanee Desai | 2024-04-19 | 2024-04-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team30G1 | 11. Accounts Payable |  | 11.02 Reviewing Bills for Goods/Services Receipt | Functional | Must have | New | Tarjanee Desai | 2024-04-19 | 2024-04-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team30G1 | 11. Accounts Payable |  | 11.03 Scheduling Payments According to Vendor Terms. | Functional | Must have | New | Tarjanee Desai | 2024-04-19 | 2024-04-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team30G1 | 11. Accounts Payable |  | 11.07 Create Supplier | Functional | Must have | New | Tarjanee Desai | 2024-04-19 | 2024-04-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team30G1 | 11. Accounts Payable |  | 11.08 Edit Supplier | Functional | Must have | New | Tarjanee Desai | 2024-04-19 | 2024-04-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team30G1 | 11. Accounts Payable |  | 11.09 Archive Supplier | Functional | Must have | New | Tarjanee Desai | 2024-04-19 | 2024-04-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0