## Sheet1
Project | Module | Release | Test Run Log Release | Test Suite | Test Run | Test Run Type | Test Case | Test Case Type | Planned Start Date | Execution Start Date | Tester | Result | Requirements | Defects (qTest)
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Tarjanee | TC9. Create Purchase Order - Field Validation "Currency" | Functional | TC9. Create Purchase Order - Field Validation "Currency" | Manual | 2024-04-18 | 2024-04-22 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Tarjanee | TC8. Create Purchase Order - Field Validation "Reference" | Functional | TC8. Create Purchase Order - Field Validation "Reference" | Manual | 2024-04-18 | 2024-04-22 | Tarjanee Desai | Failed | 1 | 1
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Tarjanee | TC10. Create Purchase Order - Field Validation "Item Description" | Functional | TC10. Create Purchase Order - Field Validation "Item Description" | Manual | 2024-04-18 | 2024-04-22 | Tarjanee Desai | Failed | 1 | 1
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Tarjanee | TC10. Create Purchase Order - Field Validation "Item Description" | Functional | TC10. Create Purchase Order - Field Validation "Item Description" | Manual | 2024-04-18 | 2024-04-22 | Tarjanee Desai | Failed | 1 | 1
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Tarjanee | TC11. Create Purchase Order - Field Validation "Quantities" | Functional | TC11. Create Purchase Order - Field Validation "Quantities" | Manual | 2024-04-18 | 2024-04-22 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Tarjanee | TC12. Create Purchase Order - Field Validation "Prices" | Functional | TC12. Create Purchase Order - Field Validation "Prices" | Manual | 2024-04-18 | 2024-04-22 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Tarjanee | TC16. Create Purchase Order - Data-Driven Defaults Testing | Functional | TC16. Create Purchase Order - Data-Driven Defaults Testing | Manual | 2024-04-18 | 2024-04-22 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Tarjanee | TC13. Create Purchase Order - Field Validation "Delivery Details" | Functional | TC13. Create Purchase Order - Field Validation "Delivery Details" | Manual | 2024-04-18 | 2024-04-22 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Tarjanee | TC14. Create Purchase Order - Entitlements Testing | Functional | TC14. Create Purchase Order - Entitlements Testing | Manual | 2024-04-18 | 2024-04-22 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Tarjanee | TC17. Create Purchase Order - Calculations Validation | Functional | TC17. Create Purchase Order - Calculations Validation | Manual | 2024-04-18 | 2024-04-22 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Tarjanee | TC15. Create Purchase Order - Data Dependency Validation "Date" and "Delivery Date" | Functional | TC15. Create Purchase Order - Data Dependency Validation "Date" and "Delivery Date" | Manual | 2024-04-18 | 2024-04-22 | Tarjanee Desai | Failed | 1 | 1
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Tarjanee | TC18. Create Purchase Order - Connectivity Testing | Functional | TC18. Create Purchase Order - Connectivity Testing | Manual | 2024-04-18 | 2024-04-22 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Tarjanee | TC19. Create Purchase Order - Data Flow-Out Testing | Functional | TC19. Create Purchase Order - Data Flow-Out Testing | Manual | 2024-04-18 | 2024-04-22 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Tarjanee | TC2. Edit Purchase Order - Core Functionality Testing | Functional | TC2. Edit Purchase Order - Core Functionality Testing | Manual | 2024-04-18 | 2024-04-22 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Tarjanee | TC8. Edit Purchase Order - Field Validation "Reference" | Functional | TC8. Edit Purchase Order - Field Validation "Reference" | Manual | 2024-04-18 | 2024-04-22 | Tarjanee Desai | Failed | 1 | 1
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Tarjanee | TC3. Edit Purchase Order - Status Validation | Functional | TC3. Edit Purchase Order - Status Validation | Manual | 2024-04-18 | 2024-04-22 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Tarjanee | TC5. Edit Purchase Order - Field Validation "Date" | Functional | TC5. Edit Purchase Order - Field Validation "Date" | Manual | 2024-04-18 | 2024-04-22 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Tarjanee | TC6. Edit Purchase Order - Field Validation "Delivery Date" | Functional | TC6. Edit Purchase Order - Field Validation "Delivery Date" | Manual | 2024-04-18 | 2024-04-22 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Tarjanee | TC4. Edit Purchase Order - Field Validation "Contact" | Functional | TC4. Edit Purchase Order - Field Validation "Contact" | Manual | 2024-04-18 | 2024-04-22 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Tarjanee | TC7. Edit Purchase Order - Field Validation "Order Number" | Functional | TC7. Edit Purchase Order - Field Validation "Order Number" | Manual | 2024-04-18 | 2024-04-22 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Tarjanee | TC9. Edit Purchase Order - Field Validation "Currency" | Functional | TC9. Edit Purchase Order - Field Validation "Currency" | Manual | 2024-04-18 | 2024-04-22 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Tarjanee | TC10. Edit Purchase Order - Field Validation "Item Description" | Functional | TC10. Edit Purchase Order - Field Validation "Item Description" | Manual | 2024-04-18 | 2024-04-22 | Tarjanee Desai | Passed | 1 | 1
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Tarjanee | TC10. Edit Purchase Order - Field Validation "Item Description" | Functional | TC10. Edit Purchase Order - Field Validation "Item Description" | Manual | 2024-04-18 | 2024-04-23 | Tarjanee Desai | Failed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Tarjanee | TC11. Edit Purchase Order - Field Validation "Quantities" | Functional | TC11. Edit Purchase Order - Field Validation "Quantities" | Manual | 2024-04-18 | 2024-04-22 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Tarjanee | TC12. Edit Purchase Order - Field Validation "Prices" | Functional | TC12. Edit Purchase Order - Field Validation "Prices" | Manual | 2024-04-18 | 2024-04-22 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Tarjanee | TC13. Edit Purchase Order - Field Validation "Delivery Details" | Functional | TC13. Edit Purchase Order - Field Validation "Delivery Details" | Manual | 2024-04-18 | 2024-04-22 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Tarjanee | TC16. Edit Purchase Order - Data-Driven Defaults Testing | Functional | TC16. Edit Purchase Order - Data-Driven Defaults Testing | Manual | 2024-04-18 | 2024-04-22 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Tarjanee | TC14. Edit Purchase Order - Entitlements Testing | Functional | TC14. Edit Purchase Order - Entitlements Testing | Manual | 2024-04-18 | 2024-04-22 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Tarjanee | TC17. Edit Purchase Order - Calculations Validation | Functional | TC17. Edit Purchase Order - Calculations Validation | Manual | 2024-04-18 | 2024-04-22 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Tarjanee | TC21. Edit Purchase Order - Data Flow-Out Testing | Functional | TC21. Edit Purchase Order - Data Flow-Out Testing | Manual | 2024-04-18 | 2024-04-22 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Tarjanee | TC15. Edit Purchase Order - Data Dependency Validation "Date" and "Delivery Date" | Functional | TC15. Edit Purchase Order - Data Dependency Validation "Date" and "Delivery Date" | Manual | 2024-04-18 | 2024-04-22 | Tarjanee Desai | Failed | 1 | 1
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Tarjanee | TC18. Edit Purchase Order - Concurrency Testing | Functional | TC18. Edit Purchase Order - Concurrency Testing | Manual | 2024-04-18 | 2024-04-22 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Tarjanee | TC20. Edit Purchase Order - Data Flow-In Testing | Functional | TC20. Edit Purchase Order - Data Flow-In Testing | Manual | 2024-04-18 | 2024-04-22 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Tarjanee | TC19. Edit Purchase Order - Connectivity Testing | Functional | TC19. Edit Purchase Order - Connectivity Testing | Manual | 2024-04-18 | 2024-04-22 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Tarjanee | TC1. Edit Purchase Order - GUI Testing | Functional | TC1. Edit Purchase Order - GUI Testing | Manual | 2024-04-18 | 2024-04-22 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Tarjanee | TC1. Create Purchase Order - GUI Testing | Functional | TC1. Create Purchase Order - GUI Testing | Manual | 2024-04-18 | 2024-04-21 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Tarjanee | TC2. Create Purchase Order - Core Functionality Testing | Functional | TC2. Create Purchase Order - Core Functionality Testing | Manual | 2024-04-18 | 2024-04-21 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Tarjanee | TC3. Create Purchase Order - Status Validation | Functional | TC3. Create Purchase Order - Status Validation | Manual | 2024-04-18 | 2024-04-21 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Tarjanee | TC4. Create Purchase Order - Field Validation "Contact" | Functional | TC4. Create Purchase Order - Field Validation "Contact" | Manual | 2024-04-18 | 2024-04-21 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Tarjanee | TC6. Create Purchase Order - Field Validation "Delivery Date" | Functional | TC6. Create Purchase Order - Field Validation "Delivery Date" | Manual | 2024-04-18 | 2024-04-21 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Tarjanee | TC7. Create Purchase Order - Field Validation "Order Number" | Functional | TC7. Create Purchase Order - Field Validation "Order Number" | Manual | 2024-04-18 | 2024-04-21 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Tarjanee | TC5. Create Purchase Order - Field Validation "Date" | Functional | TC5. Create Purchase Order - Field Validation "Date" | Manual | 2024-04-18 | 2024-04-21 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Shloka | TC2. Filter Purchase order- Core Functionality Testing | Functional | TC2. Filter Purchase order- Core Functionality Testing | Manual | 2024-04-18 | 2024-04-24 | Shloka Gupta | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Shloka | TC1. Filter Purchase Order - GUI Testing | Functional | TC1. Filter Purchase Order - GUI Testing | Manual | 2024-04-18 | 2024-04-24 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Shloka | TC3. Filter Purchase Order - Entitlements Testing | Functional | TC3. Filter Purchase Order - Entitlements Testing | Manual | 2024-04-18 | 2024-04-24 | Shloka Gupta | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Shloka | TC3. Filter Purchase Order - Entitlements Testing | Functional | TC3. Filter Purchase Order - Entitlements Testing | Manual | 2024-04-18 | 2024-04-24 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Shloka | TC4. Filter Purchase Order - Connectivity Testing | Functional | TC4. Filter Purchase Order - Connectivity Testing | Manual | 2024-04-18 | 2024-04-24 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Shloka | TC5 Approve Purchase Order - Concurrency Testing | Functional | TC5 Approve Purchase Order - Concurrency Testing | Manual | 2024-04-18 | 2024-04-29 | Shloka Gupta | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Shloka | TC4 Approve Purchase Order - Entitlements Testing | Functional | TC4 Approve Purchase Order - Entitlements Testing | Manual | 2024-04-18 | 2024-04-29 | Shloka Gupta | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Shloka | TC1. Approve Purchase Order - GUI Testing | Functional | TC1. Approve Purchase Order - GUI Testing | Manual | 2024-04-18 | 2024-04-29 | Shloka Gupta | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Shloka | TC4. Filter Purchase Order - Connectivity Testing | Functional | TC4. Filter Purchase Order - Connectivity Testing | Manual | 2024-04-18 | 2024-04-29 | Shloka Gupta | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Shloka | TC7 Approve Purchase Order - Data Flow-Out Testing | Functional | TC7 Approve Purchase Order - Data Flow-Out Testing | Manual | 2024-04-18 | 2024-04-29 | Shloka Gupta | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Shloka | Tc6 Approve Purchase Order - Connectivity Testing | Functional | Tc6 Approve Purchase Order - Connectivity Testing | Manual | 2024-04-18 | 2024-04-29 | Shloka Gupta | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Shloka | TC2 Approve a Purchase Order - Core Functionality Testing | Functional | TC2 Approve a Purchase Order - Core Functionality Testing | Manual | 2024-04-18 | 2024-04-29 | Shloka Gupta | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Shloka | TC3. Approve a Purchase Order- Status Validation | Functional | TC3. Approve a Purchase Order- Status Validation | Manual | 2024-04-18 | 2024-04-29 | Shloka Gupta | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Shloka | TC3. Filter Purchase Order - Entitlements Testing | Functional | TC3. Filter Purchase Order - Entitlements Testing | Manual | 2024-04-18 | 2024-04-29 | Shloka Gupta | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Shloka | TC2. Filter Purchase order- Core Functionality Testing | Functional | TC2. Filter Purchase order- Core Functionality Testing | Manual | 2024-04-18 | 2024-04-29 | Shloka Gupta | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Shloka | TC1. Filter Purchase Order - GUI Testing | Functional | TC1. Filter Purchase Order - GUI Testing | Manual | 2024-04-18 | 2024-04-29 | Shloka Gupta | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Shloka | Tc7 Bill Purchase Order - Data Flow-In Testing | Functional | Tc7 Bill Purchase Order - Data Flow-In Testing | Manual | 2024-04-18 | 2024-04-29 | Shloka Gupta | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Shloka | TC5 Bill Purchase Order - Concurrency Testing | Functional | TC5 Bill Purchase Order - Concurrency Testing | Manual | 2024-04-18 | 2024-04-29 | Shloka Gupta | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Shloka | Tc4 Bill Purchase Order - Entitlements Testing | Functional | Tc4 Bill Purchase Order - Entitlements Testing | Manual | 2024-04-18 | 2024-04-29 | Shloka Gupta | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Shloka | Tc3 Bill Purchase Order - Status Validation | Functional | Tc3 Bill Purchase Order - Status Validation | Manual | 2024-04-18 | 2024-04-29 | Shloka Gupta | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Shloka | Tc2 Bill Purchase Order - Core Functionality Testing | Functional | Tc2 Bill Purchase Order - Core Functionality Testing | Manual | 2024-04-18 | 2024-04-29 | Shloka Gupta | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Shloka | TC1. Bill Purchase Order - GUI Testing | Functional | TC1. Bill Purchase Order - GUI Testing | Manual | 2024-04-18 | 2024-04-29 | Shloka Gupta | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Shloka | Tc8 Bill Purchase Order - Data Flow-Out Testing | Functional | Tc8 Bill Purchase Order - Data Flow-Out Testing | Manual | 2024-04-18 | 2024-04-29 | Shloka Gupta | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Shloka | Tc8 Bill Purchase Order - Data Flow-Out Testing | Functional | Tc8 Bill Purchase Order - Data Flow-Out Testing | Manual | 2024-04-18 | 2024-04-29 | Shloka Gupta | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Shloka | Tc6 Bill Purchase Order - Connectivity Testing | Functional | Tc6 Bill Purchase Order - Connectivity Testing | Manual | 2024-04-18 | 2024-04-29 | Shloka Gupta | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Harsh | TC1. Upload Files or Add Files from the Library - GUI testing | Functional | TC1. Upload Files or Add Files from the Library - GUI testing | Manual | 2024-04-18 | 2024-04-23 | Harsh Moradiya | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Harsh | TC3. Upload Files or Add Files from the Library ET-Entitlements | Functional | TC3. Upload Files or Add Files from the Library ET-Entitlements | Manual | 2024-04-18 | 2024-04-23 | Harsh Moradiya | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Harsh | TC6. Upload Files or Add Files from the Library- CN-Connectivity | Functional | TC6. Upload Files or Add Files from the Library- CN-Connectivity | Manual | 2024-04-18 | 2024-04-23 | Harsh Moradiya | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Harsh | TC2 .Upload Files or Add Files from the Library - Core Functionality Testing | Functional | TC2 .Upload Files or Add Files from the Library - Core Functionality Testing | Manual | 2024-04-18 | 2024-04-23 | Harsh Moradiya | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Harsh | TC5. Upload Files or Add Files from the Library- CC-Concurrency | Functional | TC5. Upload Files or Add Files from the Library- CC-Concurrency | Manual | 2024-04-18 | 2024-04-23 | Harsh Moradiya | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Harsh | TC4. Upload Files or Add Files from the Library FV- field validation | Functional | TC4. Upload Files or Add Files from the Library FV- field validation | Manual | 2024-04-18 | 2024-04-23 | Harsh Moradiya | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Harsh | TC7 .Upload Files or Add Files from the Library- SI-in | Functional | TC7. Upload Files or Add Files from the Library- SI-in | Manual | 2024-04-18 | 2024-04-23 | Harsh Moradiya | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Harsh | TC3. Send Purchase Order - Entitlements | Functional | TC3. Send Purchase Order - Entitlements | Manual | 2024-04-18 | 2024-04-23 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Harsh | TC4. Send Purchase Order - Inventory Settings | Functional | TC4. Send Purchase Order - Inventory Settings | Manual | 2024-04-18 | 2024-04-23 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Harsh | TC1. Send Purchase Order - GUI Testing | Functional | TC1. Send Purchase Order - GUI Testing | Manual | 2024-04-18 | 2024-04-23 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Harsh | TC6. Send Purchase Order - Connectivity | Functional | TC6. Send Purchase Order - Connectivity | Manual | 2024-04-18 | 2024-04-23 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Harsh | TC2. Send Purchase Order - Core Functionality | Functional | TC2. Send Purchase Order - Core Functionality | Manual | 2024-04-18 | 2024-04-23 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Harsh | TC5. Send Purchase Order - CC Concurrency | Functional | TC5. Send Purchase Order - CC Concurrency | Manual | 2024-04-18 | 2024-04-23 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Harsh | TC7. Send Purchase Order - SI-Out | Functional | TC7. Send Purchase Order - SI-Out | Manual | 2024-04-18 | 2024-04-23 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Harsh | TC4. Copy Contents for a New Bill, a New Purchase Order, generating an Invoice-inventory settings | Functional | TC4. Copy Contents for a New Bill, a New Purchase Order, generating an Invoice-inventory settings | Manual | 2024-04-18 | 2024-04-23 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Harsh | TC1. Copy Contents for a New Bill, a New Purchase Order, generating an Invoice - GUI Testing | Functional | TC1. Copy Contents for a New Bill, a New Purchase Order, generating an Invoice - GUI Testing | Manual | 2024-04-18 | 2024-04-23 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Harsh | TC5. Copy Contents for a New Bill, a New Purchase Order, generating an Invoice- CC-Concurrency | Functional | TC5. Copy Contents for a New Bill, a New Purchase Order, generating an Invoice- CC-Concurrency | Manual | 2024-04-18 | 2024-04-23 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Harsh | TC3. Copy Contents for a New Bill, a New Purchase Order, generating an Invoice- entitlements | Functional | TC3. Copy Contents for a New Bill, a New Purchase Order, generating an Invoice- entitlements | Manual | 2024-04-18 | 2024-04-23 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Harsh | TC6. Copy Contents for a New Bill, a New Purchase Order, generating an Invoice- CN-Connectivity | Functional | TC6. Copy Contents for a New Bill, a New Purchase Order, generating an Invoice- CN-Connectivity | Manual | 2024-04-18 | 2024-04-23 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Harsh | TC2. Copy Contents for a New Bill, a New Purchase Order, generating an Invoice- Core Functionality Testing | Functional | TC2. Copy Contents for a New Bill, a New Purchase Order, generating an Invoice- Core Functionality Testing | Manual | 2024-04-18 | 2024-04-23 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Kalpana | TC1 View Purchase Order List - GUI Testing | Functional | TC1 View Purchase Order List - GUI Testing | Manual | 2024-04-18 | 2024-04-24 | Kalpana Komatineni | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Kalpana | TC1 View Purchase Order List - GUI Testing | Functional | TC1 View Purchase Order List - GUI Testing | Manual | 2024-04-18 | 2024-04-25 | Kalpana Komatineni | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Kalpana | TC3. View Purchase Order List - Entitlements Testing | Functional | TC3. View Purchase Order List - Entitlements Testing | Manual | 2024-04-18 | 2024-04-25 | Kalpana Komatineni | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Kalpana | TC5. View Purchase Orders - Connectivity Testing | Functional | TC5. View Purchase Orders - Connectivity Testing | Manual | 2024-04-18 | 2024-04-25 | Kalpana Komatineni | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Kalpana | TC1. Search Purchase Order - Core Functionality Testing | Functional | TC1. Search Purchase Order - Core Functionality Testing | Manual | 2024-04-18 | 2024-04-25 | Kalpana Komatineni | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Kalpana | TC2. Search Purchase Order - GUI Functionality Testing | Functional | TC2. Search Purchase Order - GUI Functionality Testing | Manual | 2024-04-18 | 2024-04-25 | Kalpana Komatineni | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Kalpana | TC4. Search Purchase Order - Connectivity Testing | Functional | TC4. Search Purchase Order - Connectivity Testing | Manual | 2024-04-18 | 2024-04-25 | Kalpana Komatineni | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Kalpana | TC2 View Purchase Order List - Core Functionality Testing | Functional | TC2 View Purchase Order List - Core Functionality Testing | Manual | 2024-04-18 | 2024-04-25 | Kalpana Komatineni | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Kalpana | TC4. View Purchase Orders - Status Testing | Functional | TC4. View Purchase Orders - Status Testing | Manual | 2024-04-18 | 2024-04-25 | Kalpana Komatineni | Passed | 1 | 0
Team30G1 | 08. Purchase Order | Cycle1 - W12 | Cycle1 - W12 | Kalpana | TC3. Search Purchase Order - Entitlements Testing | Functional | TC3. Search Purchase Order - Entitlements Testing | Manual | 2024-04-18 | 2024-04-25 | Kalpana Komatineni | Passed | 1 | 0
Team30G1 | 09. Expense Claims | Cycle2 - W13 | Cycle2 - W13 | Tarjanee | TC1. Create Expense Claim - GUI Testing | Functional | TC1. Create Expense Claim - GUI Testing | Manual | 2024-04-18 | 2024-04-28 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 09. Expense Claims | Cycle2 - W13 | Cycle2 - W13 | Tarjanee | TC5. Create Expense Claim - Field Validation "Currency" | Functional | TC5. Create Expense Claim - Field Validation "Currency" | Manual | 2024-04-18 | 2024-04-29 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 09. Expense Claims | Cycle2 - W13 | Cycle2 - W13 | Tarjanee | TC9. Create Expense Claim - Field Validation "Spent on" | Functional | TC9. Create Expense Claim - Field Validation "Spent on" | Manual | 2024-04-18 | 2024-04-29 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 09. Expense Claims | Cycle2 - W13 | Cycle2 - W13 | Tarjanee | TC2. Create Expense Claim - Core Functionality Testing | Functional | TC2. Create Expense Claim - Core Functionality Testing | Manual | 2024-04-18 | 2024-04-29 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 09. Expense Claims | Cycle2 - W13 | Cycle2 - W13 | Tarjanee | TC3. Create Expense Claim - Status Validation | Functional | TC3. Create Expense Claim - Status Validation | Manual | 2024-04-18 | 2024-04-29 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 09. Expense Claims | Cycle2 - W13 | Cycle2 - W13 | Tarjanee | TC4. Create Expense Claim - Field Validation "Purchase Amount" | Functional | TC4. Create Expense Claim - Field Validation "Purchase Amount" | Manual | 2024-04-18 | 2024-04-29 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 09. Expense Claims | Cycle2 - W13 | Cycle2 - W13 | Tarjanee | TC6. Create Expense Claim - Field Validation "Description" | Functional | TC6. Create Expense Claim - Field Validation "Description" | Manual | 2024-04-18 | 2024-04-29 | Tarjanee Desai | Failed | 1 | 1
Team30G1 | 09. Expense Claims | Cycle2 - W13 | Cycle2 - W13 | Tarjanee | TC6. Create Expense Claim - Field Validation "Description" | Functional | TC6. Create Expense Claim - Field Validation "Description" | Manual | 2024-04-18 | 2024-04-29 | Tarjanee Desai | Failed | 1 | 1
Team30G1 | 09. Expense Claims | Cycle2 - W13 | Cycle2 - W13 | Tarjanee | TC7. Create Expense Claim - Field Validation "Company Bank Account" | Functional | TC7. Create Expense Claim - Field Validation "Company Bank Account" | Manual | 2024-04-18 | 2024-04-29 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 09. Expense Claims | Cycle2 - W13 | Cycle2 - W13 | Tarjanee | TC8. Create Expense Claim - Field Validation "Spent at" | Functional | TC8. Create Expense Claim - Field Validation "Spent at" | Manual | 2024-04-18 | 2024-04-29 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 09. Expense Claims | Cycle2 - W13 | Cycle2 - W13 | Tarjanee | TC12. Create Expense Claim - Data-Driven Defaults Testing | Functional | TC12. Create Expense Claim - Data-Driven Defaults Testing | Manual | 2024-04-18 | 2024-04-29 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 09. Expense Claims | Cycle2 - W13 | Cycle2 - W13 | Tarjanee | TC12. Create Expense Claim - Data-Driven Defaults Testing | Functional | TC12. Create Expense Claim - Data-Driven Defaults Testing | Manual | 2024-04-18 | 2024-04-29 | Tarjanee Desai | Failed | 1 | 1
Team30G1 | 09. Expense Claims | Cycle2 - W13 | Cycle2 - W13 | Tarjanee | TC13. Create Expense Claim - Connectivity Testing | Functional | TC13. Create Expense Claim - Connectivity Testing | Manual | 2024-04-18 | 2024-04-29 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 09. Expense Claims | Cycle2 - W13 | Cycle2 - W13 | Tarjanee | TC10. Create Expense Claim - Field Validation "Account" | Functional | TC10. Create Expense Claim - Field Validation "Account" | Manual | 2024-04-18 | 2024-04-29 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 09. Expense Claims | Cycle2 - W13 | Cycle2 - W13 | Tarjanee | TC11. Create Expense Claim - Entitlements Testing | Functional | TC11. Create Expense Claim - Entitlements Testing | Manual | 2024-04-18 | 2024-04-29 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 09. Expense Claims | Cycle2 - W13 | Cycle2 - W13 | Tarjanee | TC14. Create Expense Claim - Data Flow-Out Testing | Functional | TC14. Create Expense Claim - Data Flow-Out Testing | Manual | 2024-04-18 | 2024-04-29 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 09. Expense Claims | Cycle2 - W13 | Cycle2 - W13 | Tarjanee | TC15. Create Expense Claim - GUI Testing - Tab Order | Functional | TC15. Create Expense Claim - GUI Testing - Tab Order | Manual | 2024-04-18 | 2024-04-29 | Tarjanee Desai | Passed | 1 | 0
Team30G1 | 09. Expense Claims | Cycle2 - W13 | Cycle2 - W13 | Shloka | TC2. Review Expense Claims - Core Functionality Testing | Functional | TC2. Review Expense Claims - Core Functionality Testing | Manual | 2024-04-18 | 2024-04-30 | Shloka Gupta | Passed | 1 | 0
Team30G1 | 09. Expense Claims | Cycle2 - W13 | Cycle2 - W13 | Shloka | TC3. Review Expense Claims - Entitlements Testing | Functional | TC3. Review Expense Claims - Entitlements Testing | Manual | 2024-04-18 | 2024-04-30 | Shloka Gupta | Passed | 1 | 0
Team30G1 | 09. Expense Claims | Cycle2 - W13 | Cycle2 - W13 | Shloka | TC5 Review Expense Claims - Data Flow-in Testing | Functional | TC5 Review Expense Claims - Data Flow-in Testing | Manual | 2024-04-18 | 2024-04-30 | Shloka Gupta | Passed | 1 | 0
Team30G1 | 09. Expense Claims | Cycle2 - W13 | Cycle2 - W13 | Shloka | TC4. Review Expense Claims- Connectivity Testing | Functional | TC4. Review Expense Claims- Connectivity Testing | Manual | 2024-04-18 | 2024-04-30 | Shloka Gupta | Passed | 1 | 0
Team30G1 | 09. Expense Claims | Cycle2 - W13 | Cycle2 - W13 | Harsh | TC3. Delete Expense Claim - Entitlements | Functional | TC3. Delete Expense Claim - Entitlements | Manual | 2024-04-18 | 2024-04-29 | Harsh Moradiya | Passed | 1 | 0
Team30G1 | 09. Expense Claims | Cycle2 - W13 | Cycle2 - W13 | Harsh | TC1. Delete Expense Claim - GUI Testing | Functional | TC1. Delete Expense Claim - GUI Testing | Manual | 2024-04-18 | 2024-04-29 | Shloka Gupta | Passed | 1 | 0
Team30G1 | 09. Expense Claims | Cycle2 - W13 | Cycle2 - W13 | Harsh | TC7 .Delete Expense Claim - Data Flow-Out Testing | Functional | TC7 .Delete Expense Claim - Data Flow-Out Testing | Manual | 2024-04-18 | 2024-04-29 | Harsh Moradiya | Passed | 1 | 0
Team30G1 | 09. Expense Claims | Cycle2 - W13 | Cycle2 - W13 | Harsh | TC2. Delete Expense Claim - Core Functionality Testing | Functional | TC2. Delete Expense Claim - Core Functionality Testing | Manual | 2024-04-18 | 2024-04-29 | Harsh Moradiya | Passed | 1 | 0
Team30G1 | 09. Expense Claims | Cycle2 - W13 | Cycle2 - W13 | Harsh | TC4 . Delete Expense Claim Concurrency | Functional | TC4 . Delete Expense Claim Concurrency | Manual | 2024-04-18 | 2024-04-29 | Harsh Moradiya | Passed | 1 | 0
Team30G1 | 09. Expense Claims | Cycle2 - W13 | Cycle2 - W13 | Harsh | TC5. Delete Expense Claim - Data flow- in | Functional | TC5. Delete Expense Claim - Data flow- in | Manual | 2024-04-18 | 2024-04-29 | Harsh Moradiya | Passed | 1 | 0
Team30G1 | 09. Expense Claims | Cycle2 - W13 | Cycle2 - W13 | Harsh | TC6 .Delete Expense Claim - Connectivity Testing | Functional | TC6 .Delete Expense Claim - Connectivity Testing | Manual | 2024-04-18 | 2024-04-29 | Harsh Moradiya | Passed | 1 | 0
Team30G1 | 09. Expense Claims | Cycle2 - W13 | Cycle2 - W13 | Kalpana | TC4. Edit Expense Claim - Field Validation "Purchase Amount" | Functional | TC4. Edit Expense Claim - Field Validation "Purchase Amount" | Manual | 2024-04-18 | 2024-04-30 | Kalpana Komatineni | Passed | 0 | 0
Team30G1 | 09. Expense Claims | Cycle2 - W13 | Cycle2 - W13 | Kalpana | TC6.Edit Expense Claim - Field Validation "Description" | Functional | TC6.Edit Expense Claim - Field Validation "Description" | Manual | 2024-04-18 | 2024-04-30 | Kalpana Komatineni | Passed | 0 | 0
Team30G1 | 09. Expense Claims | Cycle2 - W13 | Cycle2 - W13 | Kalpana | TC10. Edit Expense Claim - Field Validation "Account" | Functional | TC10. Edit Expense Claim - Field Validation "Account" | Manual | 2024-04-18 | 2024-04-30 | Kalpana Komatineni | Passed | 0 | 0
Team30G1 | 09. Expense Claims | Cycle2 - W13 | Cycle2 - W13 | Kalpana | TC11. Edit Expense Claim - Entitlements Testing | Functional | TC11. Edit Expense Claim - Entitlements Testing | Manual | 2024-04-18 | 2024-04-30 | Kalpana Komatineni | Passed | 0 | 0
Team30G1 | 09. Expense Claims | Cycle2 - W13 | Cycle2 - W13 | Kalpana | TC12. Create Expense Claim - Data-Driven Defaults Testing | Functional | TC12. Create Expense Claim - Data-Driven Defaults Testing | Manual | 2024-04-18 | 2024-04-30 | Kalpana Komatineni | Passed | 0 | 0
Team30G1 | 09. Expense Claims | Cycle2 - W13 | Cycle2 - W13 | Kalpana | TC14. Edit Expense Claim Conectivity Testing | Functional | TC14. Edit Expense Claim Conectivity Testing | Manual | 2024-04-18 | 2024-04-30 | Kalpana Komatineni | Passed | 0 | 0
Team30G1 | 09. Expense Claims | Cycle2 - W13 | Cycle2 - W13 | Kalpana | TC9. Edit Expense Claim - Field Validation "Spent on" | Functional | TC9. Edit Expense Claim - Field Validation ""Spent on" | Manual | 2024-04-18 | 2024-04-30 | Kalpana Komatineni | Passed | 0 | 0
Team30G1 | 09. Expense Claims | Cycle2 - W13 | Cycle2 - W13 | Kalpana | TC7.Edit Expense Claim - Field Validation "Company Bank Account" | Functional | TC7.Edit Expense Claim - Field Validation "Company Bank Account" | Manual | 2024-04-18 | 2024-04-30 | Kalpana Komatineni | Passed | 0 | 0
Team30G1 | 09. Expense Claims | Cycle2 - W13 | Cycle2 - W13 | Kalpana | TC15. Edit Expense Claim Data Flow-In Testing | Functional | TC15. Edit Expense Claim Data Flow-In Testing | Manual | 2024-04-18 | 2024-04-30 | Kalpana Komatineni | Passed | 0 | 0
Team30G1 | 09. Expense Claims | Cycle2 - W13 | Cycle2 - W13 | Kalpana | TC16. Edit Expense Claim Data Flow-Out Testing | Functional | TC16. Edit Expense Claim Data Flow-Out Testing | Manual | 2024-04-18 | 2024-04-30 | Kalpana Komatineni | Passed | 0 | 0
Team30G1 | 09. Expense Claims | Cycle2 - W13 | Cycle2 - W13 | Kalpana | TC16. Edit Expense Claim Data Flow-Out Testing | Functional | TC16. Edit Expense Claim Data Flow-Out Testing | Manual | 2024-04-18 | 2024-04-30 | Kalpana Komatineni | Passed | 0 | 0
Team30G1 | 09. Expense Claims | Cycle2 - W13 | Cycle2 - W13 | Kalpana | TC3. Edit Expense Claim - Status Validation | Functional | TC3. Edit Expense Claim - Status Validation | Manual | 2024-04-18 | 2024-04-30 | Kalpana Komatineni | Passed | 0 | 0
Team30G1 | 09. Expense Claims | Cycle2 - W13 | Cycle2 - W13 | Kalpana | TC8. Edit Expense Claim - Field Validation "Spent at" | Functional | TC8. Edit Expense Claim - Field Validation "Spent at" | Manual | 2024-04-18 | 2024-04-30 | Kalpana Komatineni | Passed | 0 | 0
Team30G1 | 09. Expense Claims | Cycle2 - W13 | Cycle2 - W13 | Kalpana | TC1. Edit Expense Claim - GUI Testing | Functional | TC1. Edit Expense Claim - GUI Testing | Manual | 2024-04-18 | 2024-04-30 | Kalpana Komatineni | Passed | 0 | 0
Team30G1 | 09. Expense Claims | Cycle2 - W13 | Cycle2 - W13 | Kalpana | TC13.Edit Expense Claim - Concurrency Testing | Functional | TC13.Edit Expense Claim - Concurrency Testing | Manual | 2024-04-18 | 2024-04-30 | Kalpana Komatineni | Passed | 0 | 0
Team30G1 | 09. Expense Claims | Cycle2 - W13 | Cycle2 - W13 | Kalpana | TC2. Edit Expense Claim - Core Functionality Testing | Functional | TC2. Edit Expense Claim - Core Functionality Testing | Manual | 2024-04-18 | 2024-04-30 | Kalpana Komatineni | Passed | 0 | 0
Team30G1 | 09. Expense Claims | Cycle2 - W13 | Cycle2 - W13 | Kalpana | TC5.Edit Expense Claim - Field Validation "Currency" | Functional | TC5.Edit Expense Claim - Field Validation "Currency" | Manual | 2024-04-18 | 2024-04-30 | Kalpana Komatineni | Passed | 0 | 0
Team30G1 | 09. Expense Claims | Cycle2 - W13 | Cycle2 - W13 | Shloka | TC1. Review Expense Claims - GUI Testing | Functional | TC1. Review Expense Claims - GUI Testing | Manual | 2024-04-18 | 2024-04-30 | Shloka Gupta | Passed | 1 | 0